## 1
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
1. RESEARCH AND ACTION RESEARCH
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Impact study of IT@ Schools | To Know the implementation of TALP in Schools | By using tools and techniqs while visiting the schools the information will be collected and analysed | 1) we come to know how the teachers are using technology while teaching maths and science 2) we com to know the E content developed by teachers | 0.50 lakh | Smt Rajalakshmi SrLecturer | Sept-2017 to Nov-2017
2 | Impact of 30 days English empowerment training for primary school teachers. | To know the improvement of the teachers performance level in teaching English after the training. | By using tools and techniqs while visiting the schools the information will be collected and analysed | The teachers come to know thire better performance and they also come to know thire shortfalls which are to be improved 2) They try to improve teaching skills | 0.50 lakh | Smt,Rathnamma. Sr Lecturer, | Sept-2017 to Nov-2017
| TOTAL | 2 |  |  | 1.00 lakh

## 2
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
2. RESOURCE CENTRE AND DOCUMENTATION
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Publication of Quatarly Magazines | 1) To develop the reading habit of the teachers 2) to give apportunities to the teachers to share their ideas, success stories and best practices | By publishing their articles in the magazines and distribution them to the schools. | 1) Reading habit of the teachers improves. 2) The teachers get opportunity to share their ideas, success stories and best practices. 3) The literary taste of the teachers increases. | 0.50 lakh | 1) Sri.Krishna prasad Senior Lecturer | Sept-2017 Dec-2017 Mar-2018 Jun-2018
| TOTAL |  |  |  | 0.50 lakh

## ABSTRACT
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
Programs and Activities in DIET 2017-18
Sl. No | Components | Programs Activities | Estimate (in Lakhs)
1 | Research and Action Research | Impact study of ENGLISH TRAINING & IT@ SCHOOLS (50000+50000) | 1
2 | Resource and documentation | Publishing of quarterly magazines (20000*4=80000) | 0.5
3 | Training programmes for CRP and BRP | Induction training | 3.3
4 | Technology in teacher Education | Up-gradation of existing computer labs & COMPUTER accessories | 5
5 | Content and module development | Training modules for district specific needs .Testing tools for Evaluation | 1
6 | On-site support to schools | Shaleyattha namma chittha Monitoring of training programs | 2.45
7 | Capacity building | Exposure visit to neighboring states | 2.5
8 | Innovations | Automation of library | 1
|  | Establishment of language lab | 1
17.75

## 3
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
3. Training Program for CRP and BRP
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Induction training for newly posted CRP's, BRP's, BRCO's | To develop their professional skills | By giving induction training | 1) They come to know their duties. 2) They come to know the various administrative rules and regulations and 3) They are able to discharge their duties effectively. | 110*10*300 3.30 lakh | Sri.Raghuchandra senior lecturer. | 2017-10-01
| TOTAL |  |  |  | 3.30 lakh

## 4
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
4. TECHNOLOGY IN TEACHER EDUCATION
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Up-gradation of existing computer labs | To provide better computer lab fecilities to the diet faculty as well as the teachers students | Extention of Lab.Purchasing necessary equipments and e-contents materials | 1) They get mastery over soft skills. 2) They are able to develop e- content material 3) They supervise and guide IT@ School faculty | 5.00 lakh | 1)Smt.Rajalakshmi.D.M Sr.lec | July-2017 to December-2017
| TOTAL | 1 |  |  | 5.00 lakh`

## 5
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
5. CONTENT AND MODULE DEVELOPMENT
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Training modules for Distric specific needs | to enrich our teachers | By preparing modules at Diet level | Attitudinal change | 0.5 | Sri.Krishna Prasad Sr.Lect | 2017-09-01
2 | Testing tools for Evaluation(class room observation schedule) | To guide and Feedback | Using the tool. | Improvement in teaching. | 0.5 | 1) Sri.Raghu chandra Sr.Lect | June-2017 to July-2018
| TOTAL | 1 |  |  | 1.00 lakh`

## 6
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
6.ON-SITE SUPPORT TO SCHOOLS
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Shaleyattha namma chittha Monitoring of Training programs | To know the effectiveness of the trainings and thire implemitation in the classrooms | By visiting Schools and objserving the teaching learing process and guiding the teachers | 1) Proper guidance is given to the teachers for their professional development. 2) The teaching profficiency of the teachers will be improved and it is needful for quality education for the children. | 2.45 | All Diet Faculty | April-2017 to March-2018
| TOTAL | 1 |  |  | 2.45

## 7
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
7.CAPACITY BUILDING
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Exposure visit to neighboring states | To make them aware of innovative practices undertaken in the the neighboring states. 2) To motivate them to adopt those practices in their day to day work. 3) To develop them professionally. | By Conducting exposure visit to pioneer educational institutions in the neighboring state | 1) They will adopt innovative activities and good practices in their day today work. which they objserved in thire exposer visit. 2) They plan better activities for the effective teaching. 3) Their attitude will be changed and they will thik positively to give quality education to the children | 2.5 | Sri. Umesh Shirahatti math. Sr. Lect (Diet Principal, Senior Lecturers) | 2017-12-01
| TOTAL | 2 |  |  | 2.50 lakh`

## 8
DISTRICT INSTITUTE OF EDUCATION AND TRAINING, BANGALORE RURAL
8.INNOVATIONS
Sl. No. | What | Why | How | Out Come | Estimated Expenditure | Who | When
1 | Automation of library | 1) To update the library according to the need of the hour. 2) Digitalizing the library | By Utilising the appropriate software | The diet faculty and the student teachers will be updated in technology | 1 | Smt. Usha.Lect. | Sept-2017 to January-2018
2 | Establishement of language lab | 1) To Develop better language abilities among the teachers. 2) To develop intresting in literature among the teachers. | By upgrading the computer lab and purchasing earphones, CD's E-source books and E-magazings | 1) Language skills are developed among the students. 2)students are benefited and participate actively in literary activities. | 1 | Smt.Rathnamma.Sr.Lect | Sept-2017 to February-2018
| TOTAL | 2 |  |  | 2.00lakh`
DDPI(Dev) DIET, BANGALORE RURAL.